Minutes of Meeting

Thursday March 5th 2020

Meeting opened at 19:05

1	Attendees – T Larsen, R Larsen, P Thornton, G Holmes, P Read, K Watson

Apologies  –   R Harries, Debbie Fairclough, Mark Fairclough

2	Action Point Update

20190708b	PT	Set up B Gas meeting		In progress, contacted, response received

AP	20191204	RL	To use WPPA email account	TL to link to Outlook

20200102b	PT	Contact KCom re possible sponsors	 Not accepted. To reapply?

20200106c	KW	Application to Tesco Bags For Help Awaiting Planning Permission

20201006d	RL	To contact Withernsea Harriers	Discarded

20200110	PT	Contact Wendy			W Graves, meeting re Easter. W Dunn no response

20200110	PT	Contact K Young – gig/fundraiser	ongoing

20200208a         PR/TL	Tweak RDPE EOI submission	Completed

20200208b        MF/DF  	Alma Fundraisers			ongoing

20200208c	RH	Follow up Structural Engineer lead ongoing

20200208d        TL/RH	Liaise with BW, corporate fundraising  Limited as to what can be done for us fundraising.

Contact made, ongoing, will sift TAP avenues

20200208e          ALL 	Recruit three new members each	Ongoing  -  Gifts for birthdays/Xmas?

20200210a	RL	Purchase of six collection buckets	Completed. Noted that Boatshed require small.

20200210b	PR	Forward ntl link to RH		Completed

20200210c	TL	Purchase of A3 maps		“Aged” too dark, go with Original print

20200210d	RH	Approach Precious Prints		Meetings held regarding Merchandise. Flyers for

Easter, to run Stall in Tower. Crew T shirts Easter?

20200210e	TL	Approach Larry Malkin		Ongoing

20200212	KW	Approach Nikki (Gazette) repaint 	Completed

3	Minutes of Last Meeting

Accepted

4	Matters Arising from Minutes Of Last Meeting

None raised

5	Chairman’s’ Report

a) Pier Towers. The Lease agreement has been signed, and sent to the solicitors acting on our behalf, where it was noted that there is no Break Clause. Responsible for the full 99 years

b)Planning. It was discovered K Abba (our last contact name) has moved on, D Allen is now in position. After no response to a number of emails, a reply was received 5/3/2020, stating a draft report was to be presented to ERYC meeting. TL referred back to an email from K Abba 2019, which stated “….as discussed, to commence with use, unlikely ERYC will take action if used before permission granted”

AP	c) Insurance. Quotation received from Kenneth, still awaiting Henderson’s. RL to chase up

AP	d) AGM. Meridian booked for April 2nd 2020, after considering cost options. KW to draft Agenda

e) Exhibition Space. An illustration was presented on the proposed use of the north tower, with displays, and positioning. Flat screen above door way, windows will not be impeded to full height. Discussed and approved to go ahead with necessary spend due to the (limited) time constraints on the opening

6	Secretary’s Report

Thank you letter sent to Cr Wash for Donation

UK Industrial references followed up, telephoned, contact with Mumbles, no written replies received (SAE sent)

AP	to date KW to chase up

AP	National Lottery Heritage EOI drafted, amended TL to chase Linda Clark

Apologies for lack of time, other commitments (Accepted)

AP	Issues with Expense form. KW to save as Excel 97 doc

7	Treasurer’s Report

Report circulated and discussed

Query if donation and Membership from MP received before month end – received after. TL thanked MP

BigLocal request for Easter donation of £500 to be identified as BL in accounts – noted

8	Fundraising Report

Collection Buckets – RL has a list of Buckets and locations. We need to ensure these are numbered

Possible Sponsors have approached, regarding the advertising spaces on the Viewing Platform above the beach steps (Wsea Sands, Roberts mobility). Future revenue Generation

It was noted that consent needs to be given before naming Members on Social Media. Use initials only

Funding Applications

Postcode lottery EOI submitted 4/2/2020. No response to date

RDPE EOI submitted. Advised response will be middle of May

Yorkshire Bid. Submitted amended form. Awaiting decisions

Love your high Street. Submitted

AP	Excel list of funding sources circulated. KW to draft with amounts/application/timescale windows

PR explained the Power To Change criteria for funding requirements and objectives for Community Hubs. The WPPA Business plan needs to reflect up-to-date policies and structures. PR to set out an outline plan of key

AP	points the WPPA requires to be in place, going forward. Note – Meeting to be held 14:00 22/04/2020 to discuss

9	Charity Status

Ongoing – part of the Business plan

10	Pier Towers

A report was given regarding the meeting on March 3rd 2020, set up for all groups involved in the Easter Weekend with the ERYC Foreshores. It was noted that Foreshores did NOT attend. A diagram was presented to show a number of the events/stalls/locations, with the projected activities outlined. Fifty Easter Eggs have been donated for the Easter Egg Hunt

Outlets for the Easter Flyers were discussed – include Hull Library, History Centre, ERYC?

A cut off date for financing supplies for the Towers/Easter Weekend was agreed – March 15th 2020

GH queried if we had a contingency regarding Public Gathering and the Coronavirus situation.

11	News and Media Report

AP	Holderness Heartbeat will put in the recent Press Release into the next edition. PT to draft / condense into 175

AP	worded article. Note deadline 11/03/2020. TL to resend original to PT

12	Links With Other Groups

AP	Letter received from Lions, who would like to purchase bench for the Towers. KW to reply with thanks

Noted that the NPS AGM is at Southsea in June (circulated in NPS magazine)

13 	A.O.B.

Nothing raised

12	Next Meeting

Note that the next meeting will be the WPPA Annual General Meeting

This will be held

at		The Meridian Centre

on		April 2nd 2020 19:00

Meeting closed at 21:20

Action Point Review

Colour code – Action Point Owner

DEdwards       GHolmes       TLarsen       KWatson       RHarries       RLarsen        PRead     PThornton    M&D Fairclough

20190708b	PT	Set up B Gas meeting

20191204	RL	To use WPPA email account	see 20200302

0200102b	PT	Contact KCom re possible sponsors

20200106c	KW	Application to Tesco Bags For Help

20200110	PT	Contact K Young – gig/fundraiser

20200208b        MF/DF  	Alma Fundraisers

20200208c	RH	Follow up Structural Engineer lead

20200208e          ALL 	Recruit three new members each

20200210c	TL	Purchase of A3 maps

20200210e	TL	Approach Larry Malkin

20200302	TL	Link RL WPPA to Outlook

20200305a	RL	To chase up Hendersons

20200305b	KW	Draft Agenda for A|GM

20200306a	KW	Chase up References

20200306b	TL	Chase up Linda Clark (ntlHeritage)

20200306c	KW	Save expenses as Excel 97 doc

20200308a	KW	Review/Amend Funding Source List

20200308b	PR	Structure Meeting 22/4/2020

20200311a	PT	Draft H Heartbeat article

20200311b	TL	Send PR to PT

20200312	KW	Lions Letter