Minutes of Meeting

Thursday June 4th 2020

Meeting opened at 19:03

1	Attendees – T Larsen, P Thornton, K Watson, R Larsen               (Quorum achieved)

Apologies  –   R Harries

2	Action Point Update

deferred

3	Minutes of Last Meeting

deferred

4	Matters Arising from Minutes Of Last Meeting

deferred

5	Chairman’s’ Report

The progress and work on Pier towers was covered in the email circulated on May 29th 2020. The aim is still to open the towers on June 15th, with a restricted number of stalls (one inside and one outside each tower) to maintain social distancing. The required Insurance begins on June 6th. It is planned to have the Coastal display in the North Tower, and one stall in the South. The Coastal erosion map is ready to collect, but there is some issue with timings. Assistance will be required to erect. The frame has been constructed. The Natural Birds display is ready (each approx. A3 size) – to decide on full display, or to cut out. There are twenty eight pictures showing Coastal erosion, which now need suitable captions. Banners have arrived, which can be used outside the towers dependent on wind conditions. The flat screen TV’s will be used to display local weather, and tide times, currently aa manual upload until a Wi-fi link can be arranged. These will be interspersed with the stock of images showing Withernsea and the Pier (as are on the boards at Teddy’s old site) utilising a USB port

6	Secretary’s Report

Work has started on the required H&S statement and policy, currently a draft, and certain sections can be deleted as not being applicable (Food preparation, hot drinks etc) as consumables available from the Towers will be pre-packed. A risk assessment form has been downloaded.

Work carrying on with a letter to send to Businesses asking for sponsorship – though the wording is a minefield

Piers which currently operate under a Charity status have been looked at, to see how their objects and models reflect and apply to charitable models

7	Treasurer’s Report

The accounts to date were circulated on Monday June 1st 2020, and due to the current situation do not show much advance, with the exception of the grant from Yorkshire Bid of £3879, a capital grant, recorded in deferred income funds.

The WPPA needs to consider registering for VAT, though this could mean a reduction in income on each sale, including VAT, the WPPA should be able to claim back VAT on the cost of the build.

It is advised the WPPA opt to tax the land and building (platform). VAT registration will need to start at the same time as renting stalls, so there is a need to register the WPPA from 1/6/2020.

It was put to the meeting that “The WPPA opt to tax the land and building (platform)” – Unanimously agreed

AP	RL to register the WPPA for VAT

Regarding plaques, the need to increase the price (to include VAT) was discussed, but it was agreed to leave the prices as they are at present.

8	Fundraising Report

As the grant received from Yorkshire Bid covered the full cost of items for opening the Towers, the WPPA will contact Love Your High Street regarding the offer of funds from them for some of the same items. However,

AP	following a press release from them, PT to approach and enquire for assistance in covering lost income for the period Easter (original planned opening) to date

9	Charity Status

Ongoing – part of the Business plan. Investigative work covered in Secretary’s Report

10	Pier Towers

Ongoing. Update covered in Chairman’s Report

Note – the WPPA is still paying the overheads on the Pier buildings

11	News and Media Report

deferred

12	Links With Other Groups

deferred

13 	A.O.B.

RH offered to cover the difference if the TV screens are more than the grant

KW to investigate sourcing TV screens (not immediately time-critical)

PT volunteered to help TL for assistance with displays etc

PR unable to commit to WPPA at this moment, but willing to appraise documents

The number of volunteers is noted to be thin on the ground, with those participating being stretched, however it is hoped with the opening of Pier Towers, this may increase the number, having something “real” happening

It was suggested that (for the foreseeable future) meetings be conducted via Zoom, with intermediate calls to catch up and progress on items (such as the Business Plan)

Time limit of 45 minutes advised on Zoom calls, but it is possible that this may be extended if used during “out of office hours” – i.e. evenings

14	Next Meeting

To be advised

Meeting closed at 1953

Action Point Review

Colour code – Action Point Owner

DEdwards       GHolmes       TLarsen       KWatson       RHarries       RLarsen        PRead     PThornton    M&D Fairclough

20190708b	PT	Set up B Gas meeting

20191204	RL	To use WPPA email account	see 20200302	Done

0200102b	PT	Contact KCom re possible sponsors

20200106c	KW	Application to Tesco Bags For Help 		deferred

20200110	PT	Contact K Young – gig/fundraiser

20200208b        MF/DF  	Alma Fundraisers

20200208c	RH	Follow up Structural Engineer lead			Done

20200208e          ALL 	Recruit three new members each

20200210c	TL	Purchase of A3 maps				Done

20200210e	TL	Approach Larry Malkin

20200302	TL	Link RL WPPA to Outlook

20200305a	RL	To chase up Hendersons

20200305b	KW	Draft Agenda for AGM				deferred

20200306a	KW	Chase up References				Done

20200306b	TL	Chase up Linda Clark (ntlHeritage)

20200306c	KW	Save expenses as Excel 97 doc			Done

20200308a	KW	Review/Amend Funding Source List		Done

20200308b	PR	Structure Meeting 22/4/2020

20200311a	PT	Draft Heartbeat article

20200311b	TL	Send PR to PT					Done

20200312	KW	Lions Letter					Done

20200607	RL	To register the WPPA for Vat purposes

20200308	PT	Contact “Love Your High Street”